## Assumptions
School OS SaaS - Planning Assumptions
Parameter | Baseline | Editable? | Planning Impact | Decision Status | Notes
Project start | 2026-09-21 | Yes | Drives all baseline dates | Baseline | Start after requirements baseline
Target GA | 2028-04-17 | Yes | Full production release target | Baseline | Adjust after architecture estimation
Delivery model | Two-week sprints | Yes | Sprint planning and release cadence | Confirmed | Use milestone gates between major phases
Primary client | Flutter Windows (.exe) | Yes | Desktop-first delivery | Confirmed | Architecture should keep future clients possible
Backend | Supabase / PostgreSQL | No | Database, Auth, Storage, RLS, Edge Functions | Confirmed | One Supabase project per customer school
SaaS deployment | One school = one Supabase project | No | Strong tenant isolation | Confirmed | Shared SaaS control plane
Team assumption | 1 lead engineer + part-time QA/design/SME | Yes | Dates assume lean delivery capacity | Planning assumption | Add people to compress schedule
Methodology | Agile + architecture gates | Yes | Iterative delivery with controlled schema design | Baseline | Avoid rushing irreversible database decisions
Languages | English initially | Yes | Simplifies V1 UI | Confirmed | Keep localization-ready
Deferred | GPS, biometrics, camera/face recognition, RFID/NFC, inventory, WhatsApp, payment gateway | Yes | Keeps core release achievable | Confirmed | Architecture should not block later additions

## Roadmap
School OS SaaS - Product Roadmap
Phase | Name | Start | End | Weeks | Primary Outcome | Release Gate | Owner | Status | Progress % | Dependencies | Notes
P0 | Discovery & Project Setup | 2026-09-21 | 2026-10-16 | 4 | Freeze requirements baseline, PM system, repository and standards | Requirements Baseline | Product Owner / Lead | Done | 100% | - | Master requirements complete; PM package created
P1 | Architecture & SaaS Foundation | 2026-10-19 | 2026-12-11 | 8 | Control plane design, school project template, environments, DB conventions | Architecture Gate | Lead Engineer | Done | 100% | P0 | Do not build business modules before security and migration strategy
P2 | Identity, RBAC & Academic Foundation | 2026-12-14 | 2027-02-12 | 9 | Auth/account mapping, people, roles, scopes, campuses, academic years, class structure | Foundation Alpha | Lead Engineer | Not Started | 0% | P1 | Foundation used by every later module
P3 | Students, Families & Admissions | 2027-02-15 | 2027-04-09 | 8 | Student lifecycle, family accounts, admission workflow, enrollment history, promotion | Student Core Alpha | Lead Engineer | Not Started | 0% | P2 | Historical data model must be stable
P4 | Curriculum, Teachers & Timetable | 2027-03-22 | 2027-05-14 | 8 | Subjects, curriculum, teacher assignment and timetable generation | Academic Alpha | Lead Engineer | Not Started | 0% | P2,P3 | Overlaps student work after stable entities exist
P5 | Attendance, Homework & Notifications Core | 2027-04-26 | 2027-06-25 | 9 | Morning/break attendance, QR/manual flow, corrections, assignments and base notifications | Operations Alpha | Lead Engineer | Not Started | 0% | P3,P4 | Includes offline-ready attendance contracts
P6 | Exams, Marks & Results | 2027-06-14 | 2027-08-20 | 10 | Assessment engine, grading, result approvals, locking and report cards | Academic Pilot | Lead Engineer | Not Started | 0% | P4,P5 | Exam Controller publication gate
P7 | Fees, Payments & Finance | 2027-08-09 | 2027-10-22 | 11 | Fee structures, discounts, invoices, payment evidence, receipts, reversals, overdue | School Beta | Lead Engineer | Not Started | 0% | P3,P6 | Financial integrity and approvals mandatory
P8 | HR, Payroll & Leave | 2027-10-04 | 2027-11-26 | 8 | Employees, monthly payroll, bonuses, deductions, salary approvals, configurable leave | Admin Beta | Lead Engineer | Not Started | 0% | P2,P7 | Uses shared approval engine
P9 | Library, Transport, Hostel & Medical | 2027-11-08 | 2028-01-14 | 10 | Optional operational modules with permission isolation | Feature Complete | Lead Engineer | Not Started | 0% | P3,P8 | GPS/inventory remain deferred
P10 | Offline Sync, Backup & Hardening | 2027-12-13 | 2028-02-11 | 9 | Encrypted local storage, conflict detection, backup/restore, resilience | Resilience Gate | Lead Engineer / QA | Not Started | 0% | P5,P7,P9 | No silent overwrite of critical records
P11 | Analytics, Automation & AI | 2028-01-17 | 2028-03-17 | 9 | Dashboards, reports, event automation, permission-aware AI, conversation history | Intelligence RC | Lead Engineer | Not Started | 0% | P6,P7,P10 | AI must never bypass authorization
P12 | UAT, Security, Performance & Launch | 2028-03-01 | 2028-04-14 | 7 | End-to-end validation, migration test, UAT, production runbook and release | GA Readiness | Lead Engineer / QA | Not Started | 0% | P1-P11 | Production launch after gate approval

## Task Register
Detailed Work Breakdown Structure / Master Task Register
ID | Phase | Workstream | Task / Deliverable | Start | End | Days | Owner | Priority | Status | Progress % | Dependency | Release | Acceptance / Exit Criteria | Risk Flag | Notes | Last Update
T001 | P0 | Product | Requirements discovery and question log | 2026-09-21 | 2026-09-25 | 5 | Product Owner / Lead | Critical | Done | 100% |  | Requirements Baseline | All major business questions recorded |  |  | 2026-09-19
T002 | P0 | Product | Master requirements & architecture specification v0.1 | 2026-09-28 | 2026-10-02 | 5 | Product Owner / Lead | Critical | Done | 100% | T001 | Requirements Baseline | Versioned master specification approved |  |  | 2026-09-19
T003 | P0 | PM | Project timeline, WBS, risks, RACI and governance baseline | 2026-10-05 | 2026-10-09 | 5 | Product Owner / Lead | High | Done | 100% | T002 | Requirements Baseline | PM workbook and management plan generated |  |  | 2026-09-19
T004 | P0 | Engineering | Repository layout, branching, coding standards and naming conventions | 2026-10-12 | 2026-10-16 | 5 | Lead Engineer | High | Not Started | 0% | T003 | Architecture Gate | Repository conventions documented |  |  | 2026-09-19
T005 | P1 | Architecture | Define SaaS control-plane responsibilities and school project boundaries | 2026-10-19 | 2026-10-23 | 5 | Lead Engineer | Critical | Not Started | 0% | T004 | Architecture Gate | Architecture decision recorded and testable |  |  | 2026-09-19
T006 | P1 | Architecture | Define environments: local/dev/staging/production | 2026-10-19 | 2026-10-30 | 12 | Lead Engineer | High | Not Started | 0% | T004 | Architecture Gate | Environment strategy documented |  |  | 2026-09-19
T007 | P1 | Database | Define PostgreSQL naming, IDs, timestamps, soft-delete and history conventions | 2026-10-26 | 2026-11-06 | 12 | Lead Engineer | Critical | Not Started | 0% | T005 | Architecture Gate | Database conventions approved |  |  | 2026-09-19
T008 | P1 | Database | Define migration strategy and schema-version tracking | 2026-11-02 | 2026-11-13 | 12 | Lead Engineer | Critical | Not Started | 0% | T007 | Architecture Gate | Migrations repeatable |  |  | 2026-09-19
T009 | P1 | Security | Define RLS architecture and server-side secret boundaries | 2026-11-09 | 2026-11-20 | 12 | Lead Engineer | Critical | Not Started | 0% | T007 | Architecture Gate | Default-deny security model approved |  |  | 2026-09-19
T010 | P1 | Platform | Define Storage buckets and private document access strategy | 2026-11-16 | 2026-11-27 | 12 | Lead Engineer | High | Not Started | 0% | T009 | Architecture Gate | Storage access patterns approved |  |  | 2026-09-19
T011 | P1 | Platform | Define Edge Function/service boundaries | 2026-11-23 | 2026-12-04 | 12 | Lead Engineer | High | Not Started | 0% | T009 | Architecture Gate | Server responsibilities documented |  |  | 2026-09-19
T012 | P1 | Deployment | Create reusable school-project bootstrap/migration sequence | 2026-11-30 | 2026-12-11 | 12 | Lead Engineer | Critical | Not Started | 0% | T008,T009,T010 | Architecture Gate | Fresh project can be provisioned reproducibly |  |  | 2026-09-19
T013 | P2 | Identity | Person/profile model separate from auth account | 2026-12-14 | 2026-12-24 | 11 | Lead Engineer | Critical | Not Started | 0% | T012 | Foundation Alpha | Schema + RLS tests pass |  |  | 2026-09-19
T014 | P2 | Authentication | Email/username login routing and school generated IDs | 2026-12-21 | 2027-01-08 | 19 | Lead Engineer | Critical | Not Started | 0% | T013 | Foundation Alpha | Login and identity mapping verified |  |  | 2026-09-19
T015 | P2 | RBAC | Role catalog and multiple-role account model | 2026-12-28 | 2027-01-15 | 19 | Lead Engineer | Critical | Not Started | 0% | T013 | Foundation Alpha | Multi-role switching works |  |  | 2026-09-19
T016 | P2 | RBAC | Permission actions: view/create/update/cancel/approve/export/publish | 2027-01-04 | 2027-01-22 | 19 | Lead Engineer | Critical | Not Started | 0% | T015 | Foundation Alpha | Action permissions enforced |  |  | 2026-09-19
T017 | P2 | RBAC | Scope model: campus/class/section/subject/assigned/own | 2027-01-11 | 2027-01-29 | 19 | Lead Engineer | Critical | Not Started | 0% | T016 | Foundation Alpha | Scope tests include negative cases |  |  | 2026-09-19
T018 | P2 | School Setup | School profile and configuration | 2027-01-18 | 2027-02-05 | 19 | Lead Engineer | High | Not Started | 0% | T013 | Foundation Alpha | Configuration persisted and validated |  |  | 2026-09-19
T019 | P2 | Campus | Campus entities, rooms and campus-level assignment | 2027-01-25 | 2027-02-05 | 12 | Lead Engineer | Critical | Not Started | 0% | T018 | Foundation Alpha | Campus separation enforced |  |  | 2026-09-19
T020 | P2 | Academic | Academic years, active year and historical switching | 2027-02-01 | 2027-02-12 | 12 | Lead Engineer | Critical | Not Started | 0% | T018 | Foundation Alpha | Historic years accessible |  |  | 2026-09-19
T021 | P2 | Academic | Class, section, capacity and roll-number configuration | 2027-02-01 | 2027-02-12 | 12 | Lead Engineer | Critical | Not Started | 0% | T019 | Foundation Alpha | Capacity and numbering rules validated |  |  | 2026-09-19
T022 | P3 | Students | Student core profile and statuses | 2027-02-15 | 2027-02-26 | 12 | Lead Engineer | Critical | Not Started | 0% | T020,T021 | Student Core Alpha | CRUD respects permissions |  |  | 2026-09-19
T023 | P3 | Families | Shared family account and student-family relationships | 2027-02-22 | 2027-03-05 | 12 | Lead Engineer | Critical | Not Started | 0% | T022 | Student Core Alpha | One family sees all linked children |  |  | 2026-09-19
T024 | P3 | Students | Student numbering / admission format engine | 2027-03-01 | 2027-03-12 | 12 | Lead Engineer | High | Not Started | 0% | T022 | Student Core Alpha | School-defined pattern passes validation |  |  | 2026-09-19
T025 | P3 | Admissions | Configurable admission stages and status history | 2027-03-08 | 2027-03-26 | 19 | Lead Engineer | High | Not Started | 0% | T023 | Student Core Alpha | Stages can be skipped/configured |  |  | 2026-09-19
T026 | P3 | Admissions | Application / admission documents and storage links | 2027-03-15 | 2027-04-02 | 19 | Lead Engineer | High | Not Started | 0% | T025 | Student Core Alpha | Private storage and 1MB policy applied |  |  | 2026-09-19
T027 | P3 | Enrollment | Enrollment history by year/campus/class/section/roll | 2027-03-22 | 2027-04-02 | 12 | Lead Engineer | Critical | Not Started | 0% | T022,T025 | Student Core Alpha | History never overwritten |  |  | 2026-09-19
T028 | P3 | Promotion | Promotion/repeat/manual decision workflow | 2027-03-29 | 2027-04-09 | 12 | Lead Engineer | Critical | Not Started | 0% | T027 | Student Core Alpha | New enrollment created correctly |  |  | 2026-09-19
T029 | P3 | History | Student status and important profile change history | 2027-03-29 | 2027-04-09 | 12 | Lead Engineer | High | Not Started | 0% | T022 | Student Core Alpha | Status/change history auditable |  |  | 2026-09-19
T030 | P4 | Curriculum | Subjects, subject types and custom structures | 2027-03-22 | 2027-04-02 | 12 | Lead Engineer | Critical | Not Started | 0% | T020 | Academic Alpha | Supports compulsory/optional/elective/practical |  |  | 2026-09-19
T031 | P4 | Curriculum | Curriculum by class/academic year | 2027-03-29 | 2027-04-16 | 19 | Lead Engineer | High | Not Started | 0% | T030 | Academic Alpha | Class/year curriculum mapped |  |  | 2026-09-19
T032 | P4 | Curriculum | Student optional/elective subject enrollment | 2027-04-12 | 2027-04-23 | 12 | Lead Engineer | High | Not Started | 0% | T031,T027 | Academic Alpha | Student-specific choices supported |  |  | 2026-09-19
T033 | P4 | Employees | Teacher/employee core profiles and documents | 2027-03-22 | 2027-04-09 | 19 | Lead Engineer | Critical | Not Started | 0% | T013,T018 | Academic Alpha | Employee profile and documents secured |  |  | 2026-09-19
T034 | P4 | Teaching | Teacher subject/class/section/campus assignments | 2027-04-05 | 2027-04-23 | 19 | Lead Engineer | Critical | Not Started | 0% | T033,T030 | Academic Alpha | Assignments drive authorization |  |  | 2026-09-19
T035 | P4 | Teaching | Class teacher assignment model | 2027-04-19 | 2027-04-30 | 12 | Lead Engineer | High | Not Started | 0% | T034 | Academic Alpha | One class teacher per section configurable |  |  | 2026-09-19
T036 | P4 | Timetable | Timetable periods, school hours and breaks | 2027-04-26 | 2027-05-07 | 12 | Lead Engineer | High | Not Started | 0% | T034 | Academic Alpha | Period structure configurable |  |  | 2026-09-19
T037 | P4 | Timetable | Conflict validation: teacher/room/class | 2027-05-03 | 2027-05-14 | 12 | Lead Engineer | Critical | Not Started | 0% | T036 | Academic Alpha | No double booking |  |  | 2026-09-19
T038 | P4 | Timetable | Automatic timetable generator + manual adjustment | 2027-05-03 | 2027-05-14 | 12 | Lead Engineer | High | Not Started | 0% | T036,T037 | Academic Alpha | Valid schedule generated or manual fallback |  |  | 2026-09-19
T039 | P5 | Attendance | Attendance session model: morning + optional post-break | 2027-04-26 | 2027-05-07 | 12 | Lead Engineer | Critical | Not Started | 0% | T034,T027 | Operations Alpha | School-configured sessions supported |  |  | 2026-09-19
T040 | P5 | Attendance | Manual class attendance workflow | 2027-05-03 | 2027-05-21 | 19 | Lead Engineer | Critical | Not Started | 0% | T039 | Operations Alpha | Assigned teacher/class scope enforced |  |  | 2026-09-19
T041 | P5 | Attendance | QR attendance flow and student-card token strategy | 2027-05-10 | 2027-05-28 | 19 | Lead Engineer | High | Not Started | 0% | T039 | Operations Alpha | QR identifies valid student safely |  |  | 2026-09-19
T042 | P5 | Attendance | Late, early departure, leave and status handling | 2027-05-17 | 2027-06-04 | 19 | Lead Engineer | High | Not Started | 0% | T040 | Operations Alpha | All attendance states supported |  |  | 2026-09-19
T043 | P5 | Attendance | Attendance correction approval workflow | 2027-05-24 | 2027-06-11 | 19 | Lead Engineer | Critical | Not Started | 0% | T040 | Operations Alpha | Correction retains old/new/reason/approval |  |  | 2026-09-19
T044 | P5 | Learning | Homework/assignment/project/worksheet model | 2027-05-10 | 2027-05-28 | 19 | Lead Engineer | High | Not Started | 0% | T031,T034 | Operations Alpha | Work assigned to correct audience |  |  | 2026-09-19
T045 | P5 | Learning | Student submissions, attachments, marks and feedback | 2027-05-24 | 2027-06-11 | 19 | Lead Engineer | High | Not Started | 0% | T044 | Operations Alpha | Submission lifecycle complete |  |  | 2026-09-19
T046 | P5 | Notifications | Notification inbox/read state/event interface | 2027-06-01 | 2027-06-18 | 18 | Lead Engineer | Critical | Not Started | 0% | T017 | Operations Alpha | Read/unread and event records work |  |  | 2026-09-19
T047 | P5 | Notifications | Attendance absence alerts to parents | 2027-06-14 | 2027-06-25 | 12 | Lead Engineer | High | Not Started | 0% | T040,T046 | Operations Alpha | Correct family notified |  |  | 2026-09-19
T048 | P6 | Assessment | Assessment/exam type configuration | 2027-06-14 | 2027-06-25 | 12 | Lead Engineer | Critical | Not Started | 0% | T031 | Academic Pilot | Unlimited/custom types supported |  |  | 2026-09-19
T049 | P6 | Assessment | Exam sessions, papers and custom mark components | 2027-06-21 | 2027-07-09 | 19 | Lead Engineer | Critical | Not Started | 0% | T048 | Academic Pilot | Theory/practical/custom parts supported |  |  | 2026-09-19
T050 | P6 | Assessment | Grading systems, pass rules and GPA options | 2027-06-28 | 2027-07-16 | 19 | Lead Engineer | Critical | Not Started | 0% | T049 | Academic Pilot | School-defined grading works |  |  | 2026-09-19
T051 | P6 | Marks | Teacher mark entry by assigned subject scope | 2027-07-05 | 2027-07-23 | 19 | Lead Engineer | Critical | Not Started | 0% | T034,T049 | Academic Pilot | Unauthorized subject entry blocked |  |  | 2026-09-19
T052 | P6 | Marks | Marks correction request and revision history | 2027-07-12 | 2027-07-30 | 19 | Lead Engineer | Critical | Not Started | 0% | T051 | Academic Pilot | Old/new marks and approvals retained |  |  | 2026-09-19
T053 | P6 | Results | Result calculation totals/percentage/averages/ranking | 2027-07-19 | 2027-08-06 | 19 | Lead Engineer | Critical | Not Started | 0% | T050,T051 | Academic Pilot | Calculated results validated |  |  | 2026-09-19
T054 | P6 | Results | Exam Controller review, publish and lock workflow | 2027-07-26 | 2027-08-13 | 19 | Lead Engineer | Critical | Not Started | 0% | T052 | Academic Pilot | Publish blocked until review gate passes |  |  | 2026-09-19
T055 | P6 | Results | Result card / DMC dynamic generation | 2027-08-02 | 2027-08-20 | 19 | Lead Engineer | High | Not Started | 0% | T053 | Academic Pilot | PDF generated on demand, not stored |  |  | 2026-09-19
T056 | P6 | Assessment | Online tests: MCQ/T-F/short answer/essay baseline | 2027-07-19 | 2027-08-20 | 33 | Lead Engineer | Medium | Not Started | 0% | T048,T044 | Academic Pilot | Attempt and marking lifecycle works |  |  | 2026-09-19
T057 | P7 | Finance | Fee types and fee structure engine | 2027-08-09 | 2027-08-27 | 19 | Lead Engineer | Critical | Not Started | 0% | T027 | School Beta | Fee structure configurable |  |  | 2026-09-19
T058 | P7 | Finance | Billing frequencies and student/class/campus/year fee assignment | 2027-08-16 | 2027-09-03 | 19 | Lead Engineer | Critical | Not Started | 0% | T057 | School Beta | Monthly/quarterly/half-yearly/annual/custom supported |  |  | 2026-09-19
T059 | P7 | Finance | Policy and custom discounts / scholarships | 2027-08-23 | 2027-09-10 | 19 | Lead Engineer | Critical | Not Started | 0% | T058 | School Beta | Policy + student-specific discounts work |  |  | 2026-09-19
T060 | P7 | Finance | Invoice numbering and dynamic PDF generation | 2027-08-30 | 2027-09-17 | 19 | Lead Engineer | High | Not Started | 0% | T058 | School Beta | INV-YYYY-MM-number generated uniquely |  |  | 2026-09-19
T061 | P7 | Payments | Cash/bank/wallet payment records and evidence storage | 2027-09-06 | 2027-09-24 | 19 | Lead Engineer | Critical | Not Started | 0% | T058 | School Beta | Evidence securely stored |  |  | 2026-09-19
T062 | P7 | Payments | Pending verification / approve / reject / correction flow | 2027-09-13 | 2027-10-01 | 19 | Lead Engineer | Critical | Not Started | 0% | T061 | School Beta | Unverified payment not official |  |  | 2026-09-19
T063 | P7 | Payments | Duplicate payment detection | 2027-09-20 | 2027-10-01 | 12 | Lead Engineer | High | Not Started | 0% | T061 | School Beta | Duplicates flagged |  |  | 2026-09-19
T064 | P7 | Payments | Permanent receipt numbering and dynamic receipt generation | 2027-09-27 | 2027-10-08 | 12 | Lead Engineer | Critical | Not Started | 0% | T062 | School Beta | Receipt number permanent |  |  | 2026-09-19
T065 | P7 | Finance | Partial, advance, allocation, credit and refund handling | 2027-10-04 | 2027-10-15 | 12 | Lead Engineer | Critical | Not Started | 0% | T058,T062 | School Beta | Balances reconcile after all scenarios |  |  | 2026-09-19
T066 | P7 | Finance | Overdue balance, late fee and reminder rules | 2027-10-04 | 2027-10-15 | 12 | Lead Engineer | High | Not Started | 0% | T058,T046 | School Beta | Overdue automation configurable |  |  | 2026-09-19
T067 | P7 | Finance | Financial reversal/cancellation approval and audit flow | 2027-10-11 | 2027-10-22 | 12 | Lead Engineer | Critical | Not Started | 0% | T062 | School Beta | No hard delete; reversal trace complete |  |  | 2026-09-19
T068 | P7 | Finance | Monthly/yearly collection and outstanding reports | 2027-10-11 | 2027-10-22 | 12 | Lead Engineer | High | Not Started | 0% | T058,T062 | School Beta | Reports reconcile with ledger |  |  | 2026-09-19
T069 | P8 | HR | Employee departments/designations/contracts | 2027-10-04 | 2027-10-22 | 19 | Lead Engineer | High | Not Started | 0% | T033 | Admin Beta | Employee structure complete |  |  | 2026-09-19
T070 | P8 | HR | Employee attendance and leave statuses | 2027-10-18 | 2027-11-05 | 19 | Lead Engineer | High | Not Started | 0% | T069 | Admin Beta | Attendance states validated |  |  | 2026-09-19
T071 | P8 | Leave | Configurable leave types and approval chains | 2027-10-18 | 2027-11-05 | 19 | Lead Engineer | High | Not Started | 0% | T069 | Admin Beta | School-defined approval chain works |  |  | 2026-09-19
T072 | P8 | Payroll | Monthly payroll period and salary components | 2027-10-25 | 2027-11-12 | 19 | Lead Engineer | Critical | Not Started | 0% | T069 | Admin Beta | MM-YYYY payroll supported |  |  | 2026-09-19
T073 | P8 | Payroll | Bonus/overtime/manual deduction with reason | 2027-11-01 | 2027-11-12 | 12 | Lead Engineer | High | Not Started | 0% | T072 | Admin Beta | Manual adjustments auditable |  |  | 2026-09-19
T074 | P8 | Payroll | Salary change/increment configuration and approvals | 2027-11-08 | 2027-11-19 | 12 | Lead Engineer | High | Not Started | 0% | T072 | Admin Beta | Auto/manual increment options supported |  |  | 2026-09-19
T075 | P8 | Payroll | Payroll finalization, lock and payslip generation | 2027-11-15 | 2027-11-26 | 12 | Lead Engineer | Critical | Not Started | 0% | T072,T073 | Admin Beta | Finalized payroll locked |  |  | 2026-09-19
T076 | P9 | Library | Book catalog, types, copies and availability | 2027-11-08 | 2027-11-26 | 19 | Lead Engineer | Medium | Not Started | 0% | T027 | Feature Complete | Catalog/search/availability works |  |  | 2026-09-19
T077 | P9 | Library | Borrow/return/due/fine/history for students and teachers | 2027-11-22 | 2027-12-10 | 19 | Lead Engineer | Medium | Not Started | 0% | T076 | Feature Complete | Borrow lifecycle auditable |  |  | 2026-09-19
T078 | P9 | Library | Book purchase/payment/status flow | 2027-12-06 | 2027-12-17 | 12 | Lead Engineer | Low | Not Started | 0% | T076 | Feature Complete | Purchase flow works |  |  | 2026-09-19
T079 | P9 | Transport | Vehicles, drivers, routes, stops and student assignment | 2027-11-15 | 2027-12-10 | 26 | Lead Engineer | Medium | Not Started | 0% | T027,T033 | Feature Complete | Student-route assignment works |  |  | 2026-09-19
T080 | P9 | Transport | Pickup/drop-off, transport fee link and bus attendance | 2027-12-06 | 2027-12-24 | 19 | Lead Engineer | Medium | Not Started | 0% | T079,T057 | Feature Complete | Transport fee/attendance linked |  |  | 2026-09-19
T081 | P9 | Hostel | Hostel/building/floor/room/bed model | 2027-11-29 | 2027-12-17 | 19 | Lead Engineer | Medium | Not Started | 0% | T027 | Feature Complete | Capacity/allocation structure works |  |  | 2026-09-19
T082 | P9 | Hostel | Student allocation, check-in/out, attendance and visitors | 2027-12-13 | 2028-01-07 | 26 | Lead Engineer | Medium | Not Started | 0% | T081 | Feature Complete | Hostel lifecycle works |  |  | 2026-09-19
T083 | P9 | Medical | Medical profile, allergies, vaccinations and medication alerts | 2027-12-13 | 2028-01-07 | 26 | Lead Engineer | High | Not Started | 0% | T022 | Feature Complete | Sensitive profile scoped |  |  | 2026-09-19
T084 | P9 | Medical | Nurse visits/incidents with strict permissions | 2028-01-03 | 2028-01-14 | 12 | Lead Engineer | High | Not Started | 0% | T083,T017 | Feature Complete | Unauthorized roles blocked |  |  | 2026-09-19
T085 | P10 | Offline | Offline data model and encrypted local cache | 2027-12-13 | 2028-01-07 | 26 | Lead Engineer / QA | Critical | Not Started | 0% | T040,T061 | Resilience Gate | Local data encrypted |  |  | 2026-09-19
T086 | P10 | Offline | Change queue, sync metadata and idempotency strategy | 2028-01-03 | 2028-01-21 | 19 | Lead Engineer / QA | Critical | Not Started | 0% | T085 | Resilience Gate | Duplicate sync safe |  |  | 2026-09-19
T087 | P10 | Offline | Conflict detection and administrator resolution | 2028-01-17 | 2028-02-04 | 19 | Lead Engineer / QA | Critical | Not Started | 0% | T086 | Resilience Gate | Critical conflicts never silently overwritten |  |  | 2026-09-19
T088 | P10 | Backup | Database backup/restore runbook | 2027-12-20 | 2028-01-14 | 26 | Lead Engineer / QA | High | Not Started | 0% | T012 | Resilience Gate | Restore rehearsal passes |  |  | 2026-09-19
T089 | P10 | Backup | Configuration export/import package | 2028-01-03 | 2028-01-21 | 19 | Lead Engineer / QA | High | Not Started | 0% | T088 | Resilience Gate | School config portable |  |  | 2026-09-19
T090 | P10 | Deployment | Fresh-school deployment rehearsal from zero | 2028-01-17 | 2028-02-04 | 19 | Lead Engineer / QA | Critical | Not Started | 0% | T089,T012 | Resilience Gate | New project provisioned from documented steps |  |  | 2026-09-19
T091 | P10 | Security | Storage/RLS/secret/security regression tests | 2028-01-31 | 2028-02-11 | 12 | Lead Engineer / QA | Critical | Not Started | 0% | T087 | Resilience Gate | Security regression suite passes |  |  | 2026-09-19
T092 | P11 | Analytics | Role dashboards and KPI query layer | 2028-01-17 | 2028-02-04 | 19 | Lead Engineer | High | Not Started | 0% | T053,T068,T074 | Intelligence RC | Role dashboards return authorized data |  |  | 2026-09-19
T093 | P11 | Reports | Permission-aware reporting/export framework | 2028-01-31 | 2028-02-18 | 19 | Lead Engineer | High | Not Started | 0% | T091 | Intelligence RC | Exports respect permissions |  |  | 2026-09-19
T094 | P11 | Search | Global permission-aware search | 2028-02-07 | 2028-02-25 | 19 | Lead Engineer | High | Not Started | 0% | T017,T027,T033 | Intelligence RC | Parent/teacher cannot search unauthorized students |  |  | 2026-09-19
T095 | P11 | Automation | Scheduled/event-triggered automation engine | 2028-01-31 | 2028-02-25 | 26 | Lead Engineer | High | Not Started | 0% | T046,T062 | Intelligence RC | Immediate/scheduled/event triggers work |  |  | 2026-09-19
T096 | P11 | AI | AI service layer and permission enforcement | 2028-02-14 | 2028-03-03 | 19 | Lead Engineer | Critical | Not Started | 0% | T017,T092 | Intelligence RC | AI authorization tests pass |  |  | 2026-09-19
T097 | P11 | AI | Teacher assistant / question generator | 2028-02-21 | 2028-03-10 | 19 | Lead Engineer | Medium | Not Started | 0% | T095,T031 | Intelligence RC | Teacher tools operate in assigned scope |  |  | 2026-09-19
T098 | P11 | AI | Student tutor / homework assistant | 2028-02-21 | 2028-03-10 | 19 | Lead Engineer | Medium | Not Started | 0% | T095,T044 | Intelligence RC | Student tutor scoped to student context |  |  | 2026-09-19
T099 | P11 | AI | Parent assistant / principal analytics | 2028-02-28 | 2028-03-17 | 19 | Lead Engineer | High | Not Started | 0% | T095,T091 | Intelligence RC | Role-specific analytics validated |  |  | 2026-09-19
T100 | P11 | AI | AI conversation history, retention and admin deletion | 2028-03-06 | 2028-03-17 | 12 | Lead Engineer | Medium | Not Started | 0% | T095 | Intelligence RC | Retention/delete controls work |  |  | 2026-09-19
T101 | P12 | QA | Full regression test suite | 2028-03-01 | 2028-03-24 | 24 | Lead Engineer / QA | Critical | Not Started | 0% | T020-T099 | GA Readiness | Core regression suite passes |  |  | 2026-09-19
T102 | P12 | Security | Authorization/RLS penetration and privilege-escalation testing | 2028-03-08 | 2028-03-31 | 24 | Lead Engineer / QA | Critical | Not Started | 0% | T100 | GA Readiness | No critical auth bypass |  |  | 2026-09-19
T103 | P12 | Performance | Load/performance test critical school workflows | 2028-03-08 | 2028-03-31 | 24 | Lead Engineer / QA | High | Not Started | 0% | T100 | GA Readiness | Performance targets met |  |  | 2026-09-19
T104 | P12 | UAT | School scenario UAT: admin/teacher/parent/student/accountant | 2028-03-15 | 2028-04-04 | 21 | Lead Engineer / QA | Critical | Not Started | 0% | T100 | GA Readiness | UAT accepted |  |  | 2026-09-19
T105 | P12 | Data | Migration/backup/restore and fresh deployment validation | 2028-03-22 | 2028-04-04 | 14 | Lead Engineer / QA | Critical | Not Started | 0% | T089,T100 | GA Readiness | Deployment/restore verified |  |  | 2026-09-19
T106 | P12 | Documentation | Admin guide, deployment guide, support runbook | 2028-03-15 | 2028-04-07 | 24 | Lead Engineer | High | Not Started | 0% | T100 | GA Readiness | Operational docs complete |  |  | 2026-09-19
T107 | P12 | Release | Release candidate and issue burn-down | 2028-04-01 | 2028-04-10 | 10 | Lead Engineer / QA | Critical | Not Started | 0% | T101,T102,T103,T104,T105 | GA Readiness | No open critical defects |  |  | 2026-09-19
T108 | P12 | Release | GA go/no-go review and production launch | 2028-04-11 | 2028-04-14 | 4 | Product Owner / Lead | Critical | Not Started | 0% | T106 | GA Readiness | Go/no-go signed |  |  | 2026-09-19

## Milestones
Major Milestones & Release Gates
ID | Milestone | Target Date | Phase | Deliverable | Approver | Status | Exit Criteria | Next Step
M01 | Requirements Baseline | 2026-10-16 | P0 | Master requirements + PM baseline approved | Product Owner | In Progress | No unresolved architecture blockers | Foundation may begin
M02 | Architecture Gate | 2026-12-11 | P1 | SaaS, DB, RLS, storage, migration and deployment patterns approved | Lead Engineer | Not Started | Architecture decision records complete | Foundation coding approved
M03 | Foundation Alpha | 2027-02-12 | P2 | Auth/RBAC/scope/campus/academic foundation working | Lead Engineer | Not Started | Permission tests passing | Student modules unlocked
M04 | Student Core Alpha | 2027-04-09 | P3 | Admission, family, enrollment and promotion history working | Lead Engineer | Not Started | History and transfer scenarios pass | Academic operations unlocked
M05 | Operations Alpha | 2027-06-25 | P5 | Timetable, attendance, homework and base notifications usable | Lead Engineer | Not Started | Teacher workflow UAT pass | Pilot academic operations
M06 | Academic Pilot | 2027-08-20 | P6 | Exam/marks/results/report card workflow usable | Exam Controller / Lead | Not Started | Publish-lock-correct lifecycle passes | Pilot school use
M07 | School Beta | 2027-10-22 | P7 | Finance and payments integrated with academic core | Product Owner / Lead | Not Started | Financial reconciliation passes | Broader beta
M08 | Feature Complete | 2028-01-14 | P9 | Core optional modules completed | Lead Engineer | Not Started | Module enable/disable validated | Hardening begins
M09 | Resilience Gate | 2028-02-11 | P10 | Offline sync, backup/restore and deployment rehearsal pass | Lead Engineer / QA | Not Started | Failure recovery scenarios pass | RC eligible
M10 | Intelligence RC | 2028-03-17 | P11 | Analytics, automation and permission-aware AI complete | Product Owner / Lead | Not Started | AI authorization tests pass | Release candidate
M11 | GA Readiness | 2028-04-14 | P12 | UAT, security, performance and documentation gates pass | Product Owner | Not Started | No unresolved critical defects | Approve production
M12 | General Availability | 2028-04-17 | Release | Production release | Product Owner | Not Started | Go/no-go signed | Operate/support

## Sprints
Two-Week Sprint Calendar
Sprint | Start | End | Primary Phase | Suggested Focus | Release / Gate | Status | Notes
S01 | 2026-09-21 | 2026-10-04 | P0 | Requirements, PM setup, repo standards |  | Planned
S02 | 2026-10-05 | 2026-10-18 | P0 | Requirements, PM setup, repo standards | Requirements Baseline | Planned
S03 | 2026-10-19 | 2026-11-01 | P1 | Architecture, migrations, RLS, control plane |  | Planned
S04 | 2026-11-02 | 2026-11-15 | P1 | Architecture, migrations, RLS, control plane |  | Planned
S05 | 2026-11-16 | 2026-11-29 | P1 | Architecture, migrations, RLS, control plane |  | Planned
S06 | 2026-11-30 | 2026-12-13 | P1 | Architecture, migrations, RLS, control plane | Architecture Gate | Planned
S07 | 2026-12-14 | 2026-12-27 | P2 | Auth, people, RBAC, campus, academic setup |  | Planned
S08 | 2026-12-28 | 2027-01-10 | P2 | Auth, people, RBAC, campus, academic setup |  | Planned
S09 | 2027-01-11 | 2027-01-24 | P2 | Auth, people, RBAC, campus, academic setup |  | Planned
S10 | 2027-01-25 | 2027-02-07 | P2 | Auth, people, RBAC, campus, academic setup |  | Planned
S11 | 2027-02-08 | 2027-02-21 | Launch/Support | Integration | Foundation Alpha | Planned
S12 | 2027-02-22 | 2027-03-07 | P3 | Students, family, admissions, enrollment |  | Planned
S13 | 2027-03-08 | 2027-03-21 | P3 | Students, family, admissions, enrollment |  | Planned
S14 | 2027-03-22 | 2027-04-04 | P3, P4 | Students, family, admissions, enrollment + Curriculum, teachers, timetable |  | Planned
S15 | 2027-04-05 | 2027-04-18 | P4 | Curriculum, teachers, timetable | Student Core Alpha | Planned
S16 | 2027-04-19 | 2027-05-02 | P4 | Curriculum, teachers, timetable |  | Planned
S17 | 2027-05-03 | 2027-05-16 | P4, P5 | Curriculum, teachers, timetable + Attendance, assignments, notifications |  | Planned
S18 | 2027-05-17 | 2027-05-30 | P5 | Attendance, assignments, notifications |  | Planned
S19 | 2027-05-31 | 2027-06-13 | P5 | Attendance, assignments, notifications |  | Planned
S20 | 2027-06-14 | 2027-06-27 | P5, P6 | Attendance, assignments, notifications + Exams, marks, results | Operations Alpha | Planned
S21 | 2027-06-28 | 2027-07-11 | P6 | Exams, marks, results |  | Planned
S22 | 2027-07-12 | 2027-07-25 | P6 | Exams, marks, results |  | Planned
S23 | 2027-07-26 | 2027-08-08 | P6 | Exams, marks, results |  | Planned
S24 | 2027-08-09 | 2027-08-22 | P6, P7 | Exams, marks, results + Fees, payments, finance | Academic Pilot | Planned
S25 | 2027-08-23 | 2027-09-05 | P7 | Fees, payments, finance |  | Planned
S26 | 2027-09-06 | 2027-09-19 | P7 | Fees, payments, finance |  | Planned
S27 | 2027-09-20 | 2027-10-03 | P7 | Fees, payments, finance |  | Planned
S28 | 2027-10-04 | 2027-10-17 | P7, P8 | Fees, payments, finance + HR, payroll, leave |  | Planned
S29 | 2027-10-18 | 2027-10-31 | P8 | HR, payroll, leave | School Beta | Planned
S30 | 2027-11-01 | 2027-11-14 | P8 | HR, payroll, leave |  | Planned
S31 | 2027-11-15 | 2027-11-28 | P8, P9 | HR, payroll, leave + Library, transport, hostel, medical |  | Planned
S32 | 2027-11-29 | 2027-12-12 | P9 | Library, transport, hostel, medical |  | Planned
S33 | 2027-12-13 | 2027-12-26 | P9, P10 | Library, transport, hostel, medical + Offline, backup, resilience |  | Planned
S34 | 2027-12-27 | 2028-01-09 | P9, P10 | Library, transport, hostel, medical + Offline, backup, resilience |  | Planned
S35 | 2028-01-10 | 2028-01-23 | P10 | Offline, backup, resilience | Feature Complete | Planned
S36 | 2028-01-24 | 2028-02-06 | P10, P11 | Offline, backup, resilience + Analytics, automation, AI |  | Planned
S37 | 2028-02-07 | 2028-02-20 | P11 | Analytics, automation, AI | Resilience Gate | Planned
S38 | 2028-02-21 | 2028-03-05 | P11 | Analytics, automation, AI |  | Planned
S39 | 2028-03-06 | 2028-03-19 | P11, P12 | Analytics, automation, AI + UAT, security, launch | Intelligence RC | Planned
S40 | 2028-03-20 | 2028-04-02 | P12 | UAT, security, launch |  | Planned
S41 | 2028-04-03 | 2028-04-16 | P12 | UAT, security, launch | GA Readiness | Planned
S42 | 2028-04-17 | 2028-04-17 | Launch/Support | Integration | General Availability | Planned

## Release Plan
Release Strategy
Release | Target | Audience | Included Scope | Excluded / Deferred | Entry Criteria | Exit Criteria | Rollback | Support Level | Status
R0 Internal Foundation | 2027-02-12 | Development team | Auth, RBAC, campus, academic foundation | Business modules | Architecture gate passed | Foundation automated tests pass | Revert migration in dev | Engineering only | Planned
R1 Student Alpha | 2027-04-09 | Internal + school SME | Students, family, admissions, enrollment | Finance/exams | R0 stable | Student lifecycle UAT passes | Snapshot + migration rollback | Internal | Planned
R2 Operations Alpha | 2027-06-25 | Internal pilot users | Timetable, attendance, homework, notifications | Finance/AI | R1 stable | Teacher workflows pass | Feature flag / rollback | Pilot | Planned
R3 Academic Pilot | 2027-08-20 | Selected school pilot | Exams, marks, results | Finance full suite | R2 stable | Exam lifecycle passes | Restore snapshot + app rollback | Pilot | Planned
R4 School Beta | 2027-10-22 | Broader school team | Finance/payments + core academic | Advanced optional modules | Financial test pack passes | Reconciliation/UAT pass | DB backup + app rollback | Beta | Planned
R5 Feature Complete | 2028-01-14 | Pilot customer | HR + optional modules | AI advanced | R4 stable | Module acceptance passes | Module flags + backup | Beta | Planned
R6 Release Candidate | 2028-03-17 | Production-like pilot | Offline, backup, analytics, automation, AI | Deferred features | Resilience gate passed | Zero critical defects | Full restore rehearsal | RC | Planned
R7 GA | 2028-04-17 | Production customers | Full planned release | GPS/biometrics/inventory/WhatsApp/payment gateway | GA readiness gate | Go/no-go approved | Documented production rollback | Production | Planned

## Module Scope
Module Scope & Release Mapping
Module | Category | Priority | Planned Phase | Release | Optional? | Current Decision | Key Notes
SaaS Control Plane | Platform | Critical | P1 | R0 | No | Planned | School routing, project/version metadata; no school operational data
Authentication | Foundation | Critical | P2 | R0 | No | Confirmed | Email or admin-created username; school-generated ID retained
People & Accounts | Foundation | Critical | P2 | R0 | No | Confirmed | Person separated from login; one person may have multiple roles
Roles/Permissions/Scopes | Foundation | Critical | P2 | R0 | No | Confirmed | Action + scope + approval authority
School Configuration | Foundation | Critical | P2 | R0 | No | Confirmed | Name, code, logo, currency, timezone, numbering rules
Campuses | Foundation | Critical | P2 | R0 | No | Confirmed | Separate campus scope with senior cross-campus view
Academic Years | Academic | Critical | P2 | R0 | No | Confirmed | History preserved; active-year and multi-year access
Classes/Sections/Rooms | Academic | Critical | P2 | R0 | No | Confirmed | Configurable levels, capacity, roll numbering
Students/Families | Student | Critical | P3 | R1 | No | Confirmed | Shared family account and multiple children
Admissions | Student | High | P3 | R1 | No | Confirmed | Configurable stages; some stages may be skipped
Enrollment/Promotion | Student | Critical | P3 | R1 | No | Confirmed | New enrollment record each year; preserve history
Curriculum/Subjects | Academic | Critical | P4 | R2 | No | Confirmed | Compulsory/optional/elective/practical/custom
Teachers/Assignments | Academic | Critical | P4 | R2 | No | Confirmed | Different teacher per section; multi-campus supported
Timetable | Academic | High | P4 | R2 | No | Confirmed | Automatic generation + manual adjustment
Attendance | Operations | Critical | P5 | R2 | No | Confirmed | Morning + optional break; manual/QR; correction approval
Homework/Assignments | Operations | High | P5 | R2 | No | Confirmed | Submission, feedback, marks, parent visibility
Notifications | Platform | High | P5/P11 | R2/R6 | No | Confirmed | In-app, push, email; WhatsApp later
Exams/Results | Academic | Critical | P6 | R3 | No | Confirmed | Custom assessment, approval, publish, lock
Fees/Payments | Finance | Critical | P7 | R4 | No | Confirmed | No hard delete; dynamic invoice/receipt PDFs
HR/Payroll/Leave | Administration | High | P8 | R5 | Optional | Confirmed | Monthly payroll; configurable approvals
Library | Student Life | Medium | P9 | R5 | Optional | Confirmed | Borrow/purchase/history
Transport | Student Life | Medium | P9 | R5 | Optional | Confirmed | Routes and bus attendance; GPS later
Hostel | Student Life | Medium | P9 | R5 | Optional | Confirmed | Building/floor/room/bed/student allocation
Medical | Student Life | High | P9 | R5 | Optional | Confirmed | Strict permissions
Offline Sync | Platform | Critical | P10 | R6 | No | Confirmed | Encrypted cache + conflict detection
Backup/Recovery | Platform | Critical | P10 | R6 | No | Confirmed | DB/config/deployment backup
Reports/Search/Analytics | Platform | High | P11 | R6 | No | Confirmed | Permission-aware
Automation Engine | Platform | High | P11 | R6 | No | Confirmed | Immediate/scheduled/event triggered
AI Engine | Platform | High | P11 | R6 | Optional | Confirmed | Permission-aware AI; conversations retained
Inventory | Deferred | Low | Future | Future | Optional | Deferred | Not in first priority
GPS/Biometrics/WhatsApp/Payment Gateway | Deferred | Low | Future | Future | Optional | Deferred | Architecture should not block later work

## Risks
Risk Register
ID | Risk | Category | Probability | Impact | Score | Owner | Mitigation | Trigger / Indicator | Contingency | Status | Review Date
R-01 | Scope grows faster than delivery capacity | Scope | 4 | 5 | 20 | Product Owner | Use module/release gates; defer non-core features | Frequent additions inside active sprint | Move feature to later release | Open | 2026-10-02
R-02 | Premature schema decisions create expensive migrations | Architecture | 3 | 5 | 15 | Lead Engineer | Design dependency order; ADRs; migration rehearsal | Repeated destructive migrations | Pause feature work and refactor foundation | Open | 2026-10-16
R-03 | RLS misconfiguration exposes sensitive school data | Security | 2 | 5 | 10 | Lead Engineer | Default deny; automated permission tests; security review | Unexpected cross-role access | Disable affected feature and patch policy | Open | 2026-12-11
R-04 | Offline conflicts corrupt attendance or finance | Data | 3 | 5 | 15 | Lead Engineer | Conflict detection; idempotency; no silent last-write-wins | Duplicate/conflicting sync events | Quarantine conflicts for admin resolution | Open | 2027-12-15
R-05 | Financial corrections become untraceable | Finance | 2 | 5 | 10 | Lead Engineer | No hard delete; reversal + approval + audit | Manual database edits requested | Restrict direct SQL and reconcile ledger | Open | 2027-08-15
R-06 | One-person development becomes schedule bottleneck | Resource | 4 | 4 | 16 | Product Owner | Keep priorities strict; automate testing; document architecture | Critical path slips >2 sprints | Add QA/dev support or move release date | Open | 2026-11-01
R-07 | AI reveals data user cannot normally access | AI/Security | 2 | 5 | 10 | Lead Engineer | AI uses permission-aware query/service layer | AI response contains unauthorized fields | Disable AI endpoint and audit access | Open | 2028-02-15
R-08 | Generated reports/PDFs consume excessive storage | Storage | 1 | 3 | 3 | Lead Engineer | Generate on demand; do not auto-store generated PDFs | Bucket growth exceeds plan | Purge temporary files | Open | 2027-08-01
R-09 | Uploaded documents exceed storage or performance limits | Storage | 3 | 3 | 9 | Lead Engineer | Compress/resize; 1 MB limit; structured buckets | High rejection/compression failure rate | Adjust supported file strategy | Open | 2027-03-15
R-10 | Timetable auto-generation complexity delays release | Algorithm | 3 | 3 | 9 | Lead Engineer | Manual timetable remains supported; stage optimizer | Generator fails valid schedules | Ship manual-first with assisted conflict detection | Open | 2027-04-01
R-11 | Shared family login weakens action attribution | Security | 3 | 3 | 9 | Product Owner | Treat as family role by design; log account/device/session | Dispute over who submitted action | Require confirmation for sensitive parent actions | Accepted | 2027-02-15
R-12 | Email app-password setup becomes unreliable | Integration | 3 | 3 | 9 | Lead Engineer | Abstract email provider; later support managed provider | Delivery failures/bounces | Switch provider without changing domain logic | Open | 2027-06-01
R-13 | Customer-specific customizations fork the codebase | Product | 3 | 5 | 15 | Product Owner | Use configuration/feature flags, not customer branches | One-off code requested | Reject fork; add configurable setting | Open | 2027-01-01
R-14 | Database migrations differ across school projects | Deployment | 3 | 5 | 15 | Lead Engineer | Schema version table; migration log; automated rollout checks | Different schema versions detected | Block app update until migration repaired | Open | 2027-12-01
R-15 | Backups exist but restore process is untested | Recovery | 2 | 5 | 10 | Lead Engineer / QA | Scheduled restore drills | Restore rehearsal fails | Fix runbook before GA | Open | 2028-01-01
R-16 | Performance degrades with years of attendance/results | Performance | 3 | 4 | 12 | Lead Engineer | Indexing, pagination, archival strategy, query plans | Slow dashboard/report > target | Optimize queries/indexes | Open | 2028-02-01
R-17 | Approval engine becomes too generic and difficult to maintain | Workflow | 3 | 4 | 12 | Lead Engineer | Common core + typed request handlers; avoid arbitrary JSON-only model | Many module-specific hacks | Refactor workflow contracts | Open | 2027-05-01
R-18 | Audit log volume grows rapidly | Data | 3 | 3 | 9 | Lead Engineer | Structured audit retention/partition strategy later | Audit queries slow | Archive/export old audit data under policy | Open | 2028-01-01
R-19 | School users reject workflows as too complex | UX | 3 | 4 | 12 | Product Owner / SME | Role-based dashboards, defaults, pilot feedback | Support requests for basic tasks | Simplify screens without weakening controls | Open | 2027-06-01
R-20 | Supabase plan limits or costs change | Vendor | 2 | 4 | 8 | Product Owner | Monitor usage/cost; keep portable PostgreSQL schema | Unexpected cost growth | Tune usage or revise deployment tier | Open | 2027-10-01

## RACI
RACI Responsibility Matrix
Activity | Product Owner | Lead Engineer | QA | School SME | Exam Controller | Finance/Admin | Ops/Support
Requirements & scope | A | R | C | C | C | C | I
Architecture decisions | C | A/R | C | I | I | I | I
Database schema & migrations | I | A/R | C | I | I | I | I
Security/RLS model | I | A/R | C | I | I | I | I
UX/workflow validation | A | R | C | C | C | C | I
Academic configuration | I | R | C | A/C | C | I | I
Attendance acceptance | I | R | C | A/C | I | I | I
Exam/result workflow | I | R | C | C | A | I | I
Finance workflow | I | R | C | C | I | A/C | I
HR/payroll workflow | I | R | C | C | I | A/C | I
Release testing | I | R | A | C | C | C | I
Go/no-go decision | A | R | C | C | C | C | I
Production incident response | I | A/R | R | I | I | I | R
Customer onboarding/deployment | A | R | C | C | I | I | R
Change control | A | R | C | C | C | C | I

## QA & Gates
Quality, Test & Release Gates
Area | Minimum Test Scope | When | Owner | Automate? | Blocking? | Pass Criteria | Evidence | Status | Notes
Database migrations | Fresh install + upgrade from previous schema | Every migration | Lead Engineer | Yes | Yes | Repeatable, no data loss | CI logs / migration report | Planned
RLS / authorization | Positive + negative role/scope tests | Every security change | Lead Engineer / QA | Yes | Yes | No unauthorized rows/actions | Automated test report | Planned
Audit | Sensitive actions create immutable audit trail | Per module | QA | Yes | Yes | Actor/action/time/old/new/reason captured | Audit test evidence | Planned
Approvals | Request/approve/reject/cancel/retry workflows | Per module | QA | Yes | Yes | No bypass of required approval | Workflow test report | Planned
Attendance | Morning/break/manual/QR/correction/offline | P5/P10 | QA + SME | Mixed | Yes | All attendance scenarios reconcile | Scenario checklist | Planned
Exams/results | Entry/correction/review/publish/lock | P6 | QA + Exam Controller | Mixed | Yes | Published result lifecycle correct | UAT sign-off | Planned
Finance | Invoice/payment/reversal/advance/discount/reconciliation | P7 | QA + Finance | Mixed | Yes | Ledger/report totals reconcile | Finance test pack | Planned
Payroll | Monthly calc/bonus/deduction/approval/lock | P8 | QA + Admin | Mixed | Yes | Payslip totals reconcile | Payroll test pack | Planned
Storage | Private access, compression, 1 MB policy | P3/P9 | QA | Yes | Yes | Unauthorized files inaccessible | Storage policy tests | Planned
Offline sync | Queue/idempotency/conflict resolution | P10 | QA | Yes | Yes | No silent critical overwrites | Sync stress test | Planned
Backup/restore | Restore latest backup in isolated environment | P10/P12 | Lead Engineer / QA | Mixed | Yes | Recovery runbook passes | Restore report | Planned
Performance | Key workflows at realistic school size | P12 | QA | Mixed | Yes | Targets agreed and met | Load test report | Planned
AI authorization | AI answers only from permitted data | P11/P12 | QA | Yes | Yes | No permission bypass | AI red-team cases | Planned
Accessibility/UX | Core flows usable by intended roles | Per release | QA + SME | No | No | No critical usability blockers | UAT notes | Planned
Release rollback | App + DB rollback/recovery rehearsal | R6/R7 | Lead Engineer / QA | Mixed | Yes | Rollback/recovery documented and proven | Runbook | Planned

## Change Log
Project Change & Decision Log
ID | Date | Type | Decision / Change | Reason | Impact | Approved By | Status | Version / Reference
D-001 | 2026-09-19 | Architecture | Use SaaS deployment model | Product intended for distribution | Introduces control plane and repeatable deployment | Product Owner | Approved | Requirements v0.1
D-002 | 2026-09-19 | Architecture | One school = one Supabase project | Stronger tenant isolation and simpler school RLS | Requires per-school provisioning/version management | Product Owner | Approved | Requirements v0.1
D-003 | 2026-09-19 | Architecture | Five engines: data, permission, workflow, automation, AI | Avoid disconnected CRUD architecture | Cross-cutting platform design required | Product Owner | Approved | Requirements v0.1
D-004 | 2026-09-19 | Security | Financial records are reversed/cancelled, not hard-deleted | Audit/accounting integrity | Requires correction/reversal workflows | Product Owner | Approved | Requirements v0.1
D-005 | 2026-09-19 | Product | Generated PDFs are on-demand and not auto-stored | Reduce storage consumption | Need reliable document generators | Product Owner | Approved | Requirements v0.1
D-006 | 2026-09-19 | Product | Inventory, GPS, biometrics, WhatsApp and payment gateway deferred | Control initial scope | Keep extension points only | Product Owner | Approved | Requirements v0.1
D-007 | 2026-09-21 | Architecture | Attendance core is capture-method independent; manual and QR are V1 adapters, biometric/camera/RFID/NFC are future adapters | Future attendance hardware must not force redesign of attendance history | Add source/device/event extensibility while deferring biometric/camera implementation | Product Owner | Approved | Codex Environment v0.2

## Gantt
Phase Gantt - Monthly View
[7 empty] | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30
Phase | Name | Start | End | Owner | Status | Progress % | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01
P0 | Discovery & Project Setup | 2026-09-21 | 2026-10-16 | Product Owner / Lead | In Progress | 75% | bar: 2026-09-01 to 2026-10-01
P1 | Architecture & SaaS Foundation | 2026-10-19 | 2026-12-11 | Lead Engineer | Not Started | 0% | bar: 2026-10-01 to 2026-12-01
P2 | Identity, RBAC & Academic Foundation | 2026-12-14 | 2027-02-12 | Lead Engineer | Not Started | 0% | bar: 2026-12-01 to 2027-02-01
P3 | Students, Families & Admissions | 2027-02-15 | 2027-04-09 | Lead Engineer | Not Started | 0% | bar: 2027-02-01 to 2027-04-01
P4 | Curriculum, Teachers & Timetable | 2027-03-22 | 2027-05-14 | Lead Engineer | Not Started | 0% | bar: 2027-03-01 to 2027-05-01
P5 | Attendance, Homework & Notifications Core | 2027-04-26 | 2027-06-25 | Lead Engineer | Not Started | 0% | bar: 2027-04-01 to 2027-06-01
P6 | Exams, Marks & Results | 2027-06-14 | 2027-08-20 | Lead Engineer | Not Started | 0% | bar: 2027-06-01 to 2027-08-01
P7 | Fees, Payments & Finance | 2027-08-09 | 2027-10-22 | Lead Engineer | Not Started | 0% | bar: 2027-08-01 to 2027-10-01
P8 | HR, Payroll & Leave | 2027-10-04 | 2027-11-26 | Lead Engineer | Not Started | 0% | bar: 2027-10-01 to 2027-11-01
P9 | Library, Transport, Hostel & Medical | 2027-11-08 | 2028-01-14 | Lead Engineer | Not Started | 0% | bar: 2027-11-01 to 2028-01-01
P10 | Offline Sync, Backup & Hardening | 2027-12-13 | 2028-02-11 | Lead Engineer / QA | Not Started | 0% | bar: 2027-12-01 to 2028-02-01
P11 | Analytics, Automation & AI | 2028-01-17 | 2028-03-17 | Lead Engineer | Not Started | 0% | bar: 2028-01-01 to 2028-03-01
P12 | UAT, Security, Performance & Launch | 2028-03-01 | 2028-04-14 | Lead Engineer / QA | Not Started | 0% | bar: 2028-03-01 to 2028-04-01

## Dashboard
School OS SaaS - Project Management Dashboard
Metric | Value | Phase | Status | Progress % | Weeks | Task Status | Count
Project Start | 2026-09-21 | P0 | In Progress | 75% | 4 | Not Started | 105
Target GA | 2028-04-17 | P1 | Not Started | 0% | 8 | In Progress | 0
Total Planned Tasks | 108 | P2 | Not Started | 0% | 9 | At Risk | 0
Tasks Done | 3 | P3 | Not Started | 0% | 8 | Blocked | 0
Tasks In Progress | 0 | P4 | Not Started | 0% | 8 | Done | 3
Tasks At Risk/Blocked | 0 | P5 | Not Started | 0% | 9
Overall Completion | 2.778% | P6 | Not Started | 0% | 10
Open / Mitigating Risks | 19 | P7 | Not Started | 0% | 11
High/Critical Risks (score >=15) | 6 | P8 | Not Started | 0% | 8
Next Major Gate | Architecture Gate | P9 | Not Started | 0% | 10
|  | P10 | Not Started | 0% | 9
Management Notes |  | P11 | Not Started | 0% | 9
Current focus | Freeze architecture before production schema build | P12 | Not Started | 0% | 7
Cadence | Two-week sprints; weekly risk review; milestone gate at phase end
Change rule | No major scope added to active sprint without explicit trade-off
Security rule | RLS/default-deny and approval/audit requirements are release blockers
Finance rule | No destructive deletion of financial transactions
AI rule | AI must use the same permission boundaries as the application

## README
How to Use This Project Management Workbook
Sheet | Purpose | Update Frequency | Primary Owner | What to Edit | Important Rule
Dashboard | Executive status, task counts, risks, phase progress | Weekly | Product Owner | Mostly automatic; update task/risk sheets | Do not manually overwrite KPI formulas
Roadmap | High-level phases and baseline dates | At phase planning/change approval | Product Owner / Lead | Dates, owner, status, progress | Change dates only through approved replan
Task Register | Detailed WBS and delivery tracking | Daily/weekly | Lead Engineer | Status, progress, dates, notes | Every task needs an acceptance criterion
Gantt | Monthly visual of roadmap | At roadmap change | Product Owner | Phase dates if deliberately replanned | Use as presentation view, not the detailed tracker
Sprints | Two-week sprint calendar | Every sprint | Lead Engineer | Focus, status, notes | Do not overload sprint with deferred modules
Milestones | Release and architecture gates | At gate review | Product Owner | Status and evidence | No gate passes without evidence
Release Plan | Alpha/beta/RC/GA scope | Before each release | Product Owner | Scope and criteria | Excluded scope stays excluded unless change approved
Module Scope | Module priorities and release mapping | Monthly | Product Owner | Priority/release/decision | Prevents scope creep
Risks | Risk register and mitigation | Weekly | Product Owner / Lead | Probability, impact, mitigation, status | Escalate score >=15
RACI | Responsibility matrix | When team changes | Product Owner | Responsibility cells | Keep accountability clear
QA & Gates | Quality criteria and release blockers | Per sprint/release | QA / Lead | Status/evidence/notes | Blocking tests must pass
Change Log | Architecture and scope decisions | As decisions occur | Product Owner | Add new row | Never silently overwrite major decisions
Assumptions | Planning assumptions behind dates | When assumptions change | Product Owner | Baseline assumptions | Re-estimate when capacity/scope changes

## Future Roadmap
School OS SaaS - Future / Advanced Feature Roadmap
ID | Future Feature | Domain | Priority Later | Current Status | Architecture Requirement Now | Likely Integration Pattern | Dependencies | Risk / Complexity | Notes
F-001 | Fingerprint / biometric attendance devices | Attendance | High | Deferred | Attendance core must be capture-method independent; preserve device/event IDs and source metadata | Device adapter -> validated attendance event -> attendance service | Attendance, device registry, identity mapping, sync | High | Vendor SDK/protocol differences; privacy and biometric governance required
F-002 | Camera / face-recognition attendance | Attendance | High | Deferred | Do not couple attendance table to QR/manual; allow camera-generated recognition events and confidence metadata | Camera/vision service -> recognition event -> human/rule validation -> attendance service | Attendance, device registry, media/AI service, identity mapping | Very High | Requires privacy, consent/legal review, anti-spoofing, model accuracy and hardware planning
F-003 | RFID / NFC attendance | Attendance | Medium | Deferred | Student identifiers/cards should support external token mapping | Reader adapter -> token event -> identity resolution -> attendance service | Student cards, device registry, attendance | Medium | Reader hardware and card lifecycle
F-004 | Advanced QR anti-fraud | Attendance | Medium | Deferred | QR token strategy should allow rotation/versioning and optional confirmation | Scanner -> signed/rotating token validation -> attendance | QR attendance, student cards | Medium | May add photo/device confirmation
F-005 | Live bus GPS tracking | Transport | Medium | Deferred | Transport model should use stable vehicle/route/student assignments independent of tracking provider | GPS provider adapter -> telemetry stream -> transport tracking service | Vehicles, routes, parent notifications | High | Realtime location cost, privacy, provider variance
F-006 | WhatsApp messaging | Notifications | Medium | Deferred | Notification engine must use provider/channel adapters | Notification event -> WhatsApp provider adapter | Notifications, templates, consent | Medium | Provider pricing, template approval, opt-in
F-007 | Direct payment gateway | Finance | High | Deferred | Payment ledger must support externally confirmed payments without changing financial core | Gateway webhook -> payment verification -> ledger/receipt | Payments, finance, webhook security | High | Idempotency, refunds, reconciliation
F-008 | Inventory / asset management | Operations | Medium | Deferred | No dependency required in student core; keep module boundaries clean | Optional module | Procurement/HR/rooms | Medium | Large independent domain
F-009 | IoT / smart classroom integration | Platform | Low | Deferred | Use device registry + event adapter concepts rather than embedding vendor fields | Device gateway -> event bus/service | Rooms, timetable, automation | Very High | Vendor fragmentation
F-010 | CCTV integrations | Security | Low | Deferred | Keep out of core operational schema; integrate by references/events only | External surveillance integration | Security policies | Very High | Privacy/security/legal implications
F-011 | Government reporting integrations | Reporting | Medium | Deferred | Reporting layer should expose stable canonical data views | Export/API adapters | Student, academic, finance depending jurisdiction | High | Jurisdiction-specific schemas
F-012 | External accounting integrations | Finance | Medium | Deferred | Finance records should expose stable transaction identifiers and export views | Accounting connector/export adapter | Finance ledger | High | Reconciliation and mapping
F-013 | Additional languages / RTL | UX | Medium | Deferred | No hard-coded display text in data model; localization-ready UI | Localization layer | Flutter UI | Medium | Arabic/Urdu RTL
F-014 | Voice assistant | AI | Low | Deferred | AI engine should expose service APIs independent of text UI | Voice UI -> AI service | AI permissions, speech provider | Medium | Speech privacy/cost
F-015 | Advanced predictive analytics / early-warning | AI/Analytics | High | Deferred | Preserve high-quality historical attendance/results/assignment data | Analytics feature store / model service | Attendance, results, assignments | High | Bias, explainability, model governance
F-016 | Digital certificate verification / blockchain | Documents | Low | Deferred | Generated certificate IDs and verification metadata should be stable | Verification service | Certificates, documents | Medium | Blockchain may not be necessary; keep provider-neutral