SCHOOL OS SaaS

Project Management Handbook

Execution baseline for planning, delivery, quality, release and improvement

| Version | 0.1 |
| --- | --- |
| Baseline date | 19 September 2026 |
| Project start | 21 September 2026 |
| Target GA | 17 April 2028 |
| Companion specification | School_OS_SaaS_Master_Specification_v0.1 |

Living document - improve by versioning, not by silently replacing decisions.

# Contents

1. Purpose and project context

2. Delivery assumptions

3. Scope map

4. Product and architecture principles

5. Master timeline

6. Release strategy and milestones

7. Delivery cadence and work rules

8. Governance, RACI and change control

9. Quality, security and data management

10. SaaS deployment and environment strategy

11. Testing and defect management

12. Risk management

13. Documentation, reporting and KPIs

14. Pilot, UAT, release and operations

15. Improvement backlog

Appendices - management checklists and package files

# 1. Purpose and project context

This handbook is the execution companion to the School OS SaaS Master Specification. It defines how the product is planned, sequenced, built, tested, reviewed, released, supported and improved. It is not the database schema; it is the management system that controls the work leading to that schema and product.

The product is a configurable School Operating System built around five cross-cutting engines: Data, Permission, Workflow, Automation and AI. The management approach protects those principles while allowing iterative releases.

# 2. Delivery assumptions

One customer school uses one Supabase project for strong tenant isolation.

A separate SaaS control plane tracks customers/projects/subscriptions/versions and does not hold school operational data.

Flutter Windows (.exe) is the first desktop client.

Supabase/PostgreSQL provides database, Auth, Storage, RLS and server-side functions/services.

Two-week sprints are used, with architecture and release gates.

Baseline dates assume one lead engineer with part-time QA/design/domain support.

English is initial language; localization is kept possible.

Generated PDFs are created on demand rather than auto-stored.

Financial transactions are reversed/cancelled, never casually hard-deleted.

GPS, biometrics, inventory, WhatsApp and external payment gateway are deferred.

# 3. Scope map

| Area | Included capability |
| --- | --- |
| Foundation | SaaS control plane, authentication, people/accounts, RBAC, scopes, school config, campuses, academic years, classes/sections/rooms |
| Student Core | Students, families, admissions, enrollment, transfers, promotion, student status/history, documents |
| Academic | Curriculum, subjects, teachers, teacher assignments, timetable, attendance, homework, assessments, marks, results |
| Finance | Fee types/structures, discounts, invoice data, payments, verification, receipts, advance/partial payments, credit/refund, reversals, reports |
| Administration | HR, employee attendance, leave, payroll, contracts, documents and approvals |
| Student Life | Library, transport, hostel and medical |
| Platform | Approval engine, audit, notifications, search, analytics, automation, AI, offline sync, backup/recovery |
| Deferred | GPS, biometrics, inventory, WhatsApp and external payment gateway |

# 4. Product and architecture principles

History over overwrite: preserve academic, financial, result, status and audit history.

Permission is not authority: users may be allowed to request a change without applying it directly.

Approval is reusable: sensitive changes use a central workflow/approval model.

Audit is mandatory: sensitive actions, including Super Admin actions, are traceable.

Default-deny security: access is explicitly granted through role, action and scope.

AI obeys the same permission boundaries as the normal application.

Configuration beats customer code forks.

Database changes are controlled, versioned migrations.

Each school project must be reproducible from deployment documentation.

Offline sync is conflict-aware and does not silently overwrite critical records.

# 5. Master timeline

| Phase | Name | Start | End | Gate |
| --- | --- | --- | --- | --- |
| P0 | Discovery & Project Setup | 2026-09-21 | 2026-10-16 | Requirements Baseline |
| P1 | Architecture & SaaS Foundation | 2026-10-19 | 2026-12-11 | Architecture Gate |
| P2 | Identity, RBAC & Academic Foundation | 2026-12-14 | 2027-02-12 | Foundation Alpha |
| P3 | Students, Families & Admissions | 2027-02-15 | 2027-04-09 | Student Core Alpha |
| P4 | Curriculum, Teachers & Timetable | 2027-03-22 | 2027-05-14 | Academic Alpha |
| P5 | Attendance, Homework & Notifications Core | 2027-04-26 | 2027-06-25 | Operations Alpha |
| P6 | Exams, Marks & Results | 2027-06-14 | 2027-08-20 | Academic Pilot |
| P7 | Fees, Payments & Finance | 2027-08-09 | 2027-10-22 | School Beta |
| P8 | HR, Payroll & Leave | 2027-10-04 | 2027-11-26 | Admin Beta |
| P9 | Library, Transport, Hostel & Medical | 2027-11-08 | 2028-01-14 | Feature Complete |
| P10 | Offline Sync, Backup & Hardening | 2027-12-13 | 2028-02-11 | Resilience Gate |
| P11 | Analytics, Automation & AI | 2028-01-17 | 2028-03-17 | Intelligence RC |
| P12 | UAT, Security, Performance & Launch | 2028-03-01 | 2028-04-14 | GA Readiness |

The detailed workbook breaks this roadmap into 108 tasks and 42 two-week sprints with owners, dependencies, priorities, acceptance criteria, progress tracking and release mapping.

# 6. Release strategy and milestones

## 6.1 Release sequence

| Release | Name | Scope |
| --- | --- | --- |
| R0 | Internal Foundation | Identity/RBAC/campus/academic foundations. |
| R1 | Student Alpha | Students, family, admissions and enrollment. |
| R2 | Operations Alpha | Timetable, attendance, homework and notifications. |
| R3 | Academic Pilot | Exams, marks and results. |
| R4 | School Beta | Fees, payments and financial controls. |
| R5 | Feature Complete | HR and optional operational modules. |
| R6 | Release Candidate | Offline, backup, analytics, automation and AI. |
| R7 | General Availability | Production release after all blocking gates. |

## 6.2 Major milestones

| ID | Milestone | Target | Exit intent |
| --- | --- | --- | --- |
| M01 | Requirements Baseline | 2026-10-16 | Requirements and PM baseline approved. |
| M02 | Architecture Gate | 2026-12-11 | SaaS, DB, RLS, storage, migrations and deployment patterns approved. |
| M03 | Foundation Alpha | 2027-02-12 | Authentication, RBAC, scope, campus and academic foundation working. |
| M04 | Student Core Alpha | 2027-04-09 | Admissions, family, enrollment and promotion history working. |
| M05 | Operations Alpha | 2027-06-25 | Timetable, attendance, homework and base notifications usable. |
| M06 | Academic Pilot | 2027-08-20 | Exam, marks, results and result card lifecycle usable. |
| M07 | School Beta | 2027-10-22 | Finance/payments integrated with academic core. |
| M08 | Feature Complete | 2028-01-14 | Core optional modules completed. |
| M09 | Resilience Gate | 2028-02-11 | Offline sync, backup/restore and deployment rehearsal pass. |
| M10 | Intelligence RC | 2028-03-17 | Analytics, automation and permission-aware AI complete. |
| M11 | GA Readiness | 2028-04-14 | UAT, security, performance and documentation gates pass. |
| M12 | General Availability | 2028-04-17 | Production release. |

# 7. Delivery cadence and work rules

## 7.1 Cadence

Sprint length: 2 weeks.

Sprint planning: select dependency-ready work under a single sprint goal.

Weekly risk/decision/security/migration review.

Sprint review/demo against acceptance criteria.

Sprint retrospective and improvement actions.

Phase gate before treating foundations as stable.

Release gate before external/pilot/production promotion.

## 7.2 Definition of Ready

A task is Ready when the objective, owner, dependencies, acceptance criteria, permission/data impact and test expectation are understood. Schema work must also describe naming/history/RLS implications.

## 7.3 Definition of Done

Done requires implementation, migrations where applicable, authorization/RLS, tests, audit/approval behavior where applicable, documentation and acceptance criteria. UI completion alone is not Done.

## 7.4 Priority rules

| Priority | Meaning |
| --- | --- |
| Critical | Security/data-integrity/release blocker. |
| High | Required for planned release or core workflow. |
| Medium | Important but can move without invalidating core release. |
| Low | Optional/deferred enhancement. |

# 8. Governance, RACI and change control

## 8.1 Core responsibilities

Product Owner - scope, sequencing, value, change approval and go/no-go.

Lead Engineer - architecture, schema, migrations, implementation, technical quality and security.

QA - test strategy, regression, negative authorization tests, evidence and release quality.

School SME - workflow realism and usability validation.

Exam Controller - acceptance of result review/publish controls.

Finance/Admin SME - validation of fees, payments, payroll and reconciliation.

Operations/Support - onboarding, deployments, production support and incidents.

## 8.2 Change control

Major scope, architecture, security, financial-integrity and release decisions are added to the Change Log. Approved decisions are never silently overwritten; a later decision supersedes them with a new record. A major scope addition during an active sprint requires an explicit trade-off: remove equivalent work, move the addition, add capacity, or move the date.

# 9. Quality, security and data management

## 9.1 Quality gates

Repeatable fresh-install and upgrade migrations.

Positive and negative RLS/authorization tests.

Audit tests for sensitive actions.

Approval-workflow bypass tests.

Attendance reconciliation including corrections and offline behavior.

Result entry/correction/review/publish/lock lifecycle.

Finance reconciliation across discounts, advance/partial payments and reversals.

Private Storage access and document-size controls.

Offline idempotency/conflict tests.

Backup/restore rehearsal.

AI authorization tests.

Release rollback/recovery rehearsal.

## 9.2 Security model

Authorization is modeled as Role + Permission Action + Scope + Approval Authority. Client applications never contain service-role/database/SMTP/AI secrets. UI visibility is not considered a security control; server-side/RLS enforcement is mandatory.

## 9.3 Data integrity

Preserve historical enrollment/status/result/financial/audit records.

No hard deletion of official financial transactions.

Published results require controlled correction/revision.

Sensitive correction workflows retain old value, new value, reason, actor and approval.

Schema changes use migrations; released migrations are not casually edited.

# 10. SaaS deployment and environment strategy

## 10.1 Tenant model

The chosen architecture is one school = one Supabase project. The shared control plane stores routing, project metadata, plans/modules and app/schema versions. Student, employee, finance, medical and other operational data remains in the school project.

## 10.2 Deployment sequence

1.  Create Supabase project.

2.  Configure environment and server-side secrets.

3.  Run versioned database migrations.

4.  Configure Storage buckets and access policies.

5.  Deploy server functions/services.

6.  Create initial Super Admin.

7.  Run school setup/configuration.

8.  Run smoke/security checks.

9.  Record deployed schema/app version in control plane.

10.  Activate school tenant.

## 10.3 Environments

| Environment | Purpose |
| --- | --- |
| Local/Development | Rapid engineering using disposable data. |
| Staging/QA | Production-like schema, controlled test data and release validation. |
| Production | Customer school project; migrations only through controlled release procedure. |

# 11. Testing and defect management

## 11.1 Test layers

Unit/domain logic tests.

Database constraints and migration tests.

RLS/authorization tests including denied cases.

Service/Edge Function tests.

Flutter integration tests.

End-to-end scenario tests.

UAT with realistic school roles.

Security/performance/recovery tests before GA.

## 11.2 High-value scenario packs

Admission -> enrollment -> promotion/transfer; teacher assignment and scope; morning/QR attendance and correction; exam marks -> correction -> Exam Controller review -> publish -> lock; discounts/advance/partial payment -> verification -> receipt -> reversal; payroll finalization; family account; medical privacy; offline conflict; backup/restore; AI authorization.

## 11.3 Defect severity

| Severity | Definition | Release impact |
| --- | --- | --- |
| S1 Critical | Security breach, data loss/corruption, finance/result integrity failure, core workflow unusable. | Blocks release. |
| S2 High | Major workflow broken with no acceptable workaround. | Normally blocks release. |
| S3 Medium | Functional defect with workaround. | Schedule according to release impact. |
| S4 Low | Cosmetic or minor usability issue. | Does not normally block release. |

# 12. Risk management

| ID | Risk | Score | Primary mitigation |
| --- | --- | --- | --- |
| R-01 | Scope grows faster than delivery capacity | 20 | Use release gates; defer non-core features; require trade-offs for additions. |
| R-02 | Premature schema decisions create expensive migrations | 15 | Use dependency-first design, ADRs, migration rehearsal and architecture gate. |
| R-03 | RLS misconfiguration exposes sensitive data | 10 | Default-deny RLS, positive/negative authorization tests and security review. |
| R-04 | Offline conflicts corrupt attendance or finance | 15 | Idempotent sync, conflict detection and administrator resolution; no silent overwrite. |
| R-05 | Financial corrections become untraceable | 10 | No hard deletion; use reversal/cancellation, reason, approval and audit. |
| R-06 | Lean team becomes delivery bottleneck | 16 | Strict priorities, test automation, documentation and additional QA/dev support when needed. |
| R-07 | AI reveals unauthorized data | 10 | Permission-aware AI service layer; AI never bypasses normal authorization. |
| R-13 | Customer customization forks codebase | 15 | Configuration and feature flags only; avoid customer-specific code branches. |
| R-14 | Schema versions differ across school projects | 15 | Schema-version table, migration logs and controlled rollout checks. |
| R-15 | Backups exist but restore is untested | 10 | Scheduled restore drills and GA blocking recovery rehearsal. |

Scores 15+ require explicit weekly attention. The complete editable risk register is maintained in the Excel workbook.

# 13. Documentation, reporting and KPIs

## 13.1 Required documentation

Master product requirements.

Architecture decision records.

Schema/data dictionary.

Migration notes and schema versioning.

RLS/permission matrix.

Service contracts.

Deployment and backup/restore guides.

Admin and role-based user guides.

Release notes and known issues.

Support/incident runbook.

## 13.2 Weekly status report

Report completed work, current sprint goal, next milestone, overall completion, blockers, top risks, architecture decisions, security/data-integrity concerns, defects by severity and any scope/date changes. The Excel Dashboard is the numerical source; the narrative should explain deviations and decisions.

## 13.3 Execution KPIs

Sprint goal completion rate.

Critical/high tasks completed vs planned.

Open blocker count and age.

High-risk count and trend.

Escaped defects by severity.

Authorization/RLS test pass rate.

Migration success rate.

UAT scenario pass rate.

Backup/restore rehearsal success.

Schema-version consistency across school projects.

# 14. Pilot, UAT, release and operations

## 14.1 Pilot/UAT

Pilot coverage should include Super Admin/Owner/Principal, campus admin, teacher, Exam Controller, accountant, parent, student and optional-module roles. UAT uses realistic end-to-end school scenarios. Feedback is classified as defect, usability improvement, configuration need or new scope.

## 14.2 Release procedure

1.  Freeze the migration/release set.

2.  Back up and confirm recovery path.

3.  Validate app/schema compatibility.

4.  Run blocking QA/security/data-integrity tests.

5.  Publish release notes.

6.  Migrate in controlled order and confirm schema version.

7.  Run smoke tests for critical roles/workflows.

8.  Monitor and record release health.

9.  If blocking failure occurs, use documented rollback/recovery; do not improvise irreversible SQL.

## 14.3 Post-GA operations

Operate with incident severity, controlled release channels, per-school version tracking, recurring restore drills, security review, cost/storage monitoring, performance monitoring and a managed backlog. Customer-specific requests should become configurable product features rather than private code forks.

# 15. Improvement backlog

Version 0.1 is a baseline. Later versions may add effort points, budget/cost control, automated CI/CD provisioning, SLA/support metrics, telemetry/observability targets, licensing/subscription automation, multilingual delivery, mobile clients and the deferred GPS/biometrics/inventory/WhatsApp/payment-gateway capabilities once the core platform is stable.

# Appendix A - Weekly / Sprint / Gate Checklists

## Weekly

Update task status/progress/notes.

Review blockers and high risks.

Review migration/RLS/security changes.

Confirm sprint goal remains realistic.

Record major decisions in Change Log.

## Sprint end

Demo completed behavior.

Confirm acceptance criteria and tests.

Close or re-plan incomplete tasks.

Update milestone/release confidence.

Record retrospective improvements.

## Phase gate

Confirm blocking exit criteria.

Confirm dependent schema/contracts are stable enough.

Review security, migration and backup impact.

Approve next phase or record remaining conditions.

## Release

Blocking tests pass.

Migration and recovery plan ready.

Release notes complete.

UAT sign-off where required.

No unresolved Severity 1 defects.

Go/no-go recorded.

# Appendix B - Package files

School_OS_SaaS_Project_Management_Master_v0.1.xlsx - detailed workbook with dashboard, roadmap, WBS, sprints, releases, milestones, risks, RACI, QA gates and change log.

School_OS_SaaS_Project_Management_Handbook_v0.1.md - editable source.

School_OS_SaaS_Project_Management_Handbook_v0.1.docx - formatted execution handbook.

School_OS_SaaS_Project_Management_Handbook_v0.1.pdf - share/presentation version.

School_OS_SaaS_Master_Specification_v0.1.* - requirements and architecture baseline.